## ProductBacklog
PRODUCT BACKLOG
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Patient | Register Myself Using Phone Number | I Can Receive A Confirmation/Verification Message | 1 | CK
1 | SB1/US2 | Patient | Register Myself Using Personal Detail | I Can Register My Self | 1 | PK
1 | SB1/US3 | Patient | Receive A Confirmation Message/OTP | I Can Access The Qurative.ai System | 1 | DM
1 | SB1/US4 | Patient | Login Into The System Using EMail Id And Password | I Can Succesfully Login To The System | 1 | CK
1 | SB1/US5 | Patient | Write Comments | I Can Share My Experience | 1 | PK
1 | SB1/US6 | Patient | Get Contact Support | I Can Ask My Query | 1 | DM
1 | SB1/US7 | Patient | Know About System Developer | I Can Know Them | 1 | CK
1 | SB1/US8 | Patient | Have A Responsive Web-System | I Can Access It In Different Resolution Devices | 1 | PK
1 | SB1/US9 | Patient | Know About Term And Condition Of Product | I Am Aware Of System Usage Policy | 1 | DM
1 | SB1/US10 | Patient | Have Optimized WebSystem | It Works In Low Internet Connection Also | 1 | CK
1 | SB1/US11 | Patient | Have Description For All Chest Disease | Patient Can I Can Understand Disease Well | 1 | PK
1 | SB1/US12 | Patient | Have SSL Encrypted WebSystem | Access Is Secure | 4 | DM
1 | SB1/US13 | Patient | Upload My Chest X-Ray Image | I Can Detect Dieseas If Exist | 3 | CK
1 | SB1/US14 | Patient | Have Separate Prediction | I Can Easily See Result Of All Dieseas | 3 | PK
1 | SB1/US15 | Patient | Analyze Chest X-Ray | I Can Identify Covid19 | 3 | DM
1 | SB1/US16 | Patient | Know The Reason For Covid | I Can Confirm The Covid | 3 | CK
1 | SB1/US17 | Patient | Have Separate Report For Covid | I Can Show It To Others | 3 | PK
1 | SB1/US18 | Patient | Download The Report Of Covid | I Can Show It To Others | 3 | DM
1 | SB1/US19 | Patient | Analyze Chest X-Ray | I Can Identify Atelectasis | 3 | CK
2 | SB2/US1 | Patient | Analyze Chest X-Ray | I Can Identify Consolidation | 3 | PK
2 | SB2/US2 | Patient | Analyze Chest X-Ray | I Can Identify Infiltration | 3 | DM
2 | SB2/US3 | Patient | Analyze Chest X-Ray | I Can Identify Pneumothorax | 3 | CK
2 | SB2/US4 | Patient | Analyze Chest X-Ray | I Can Identify Edema | 3 | PK
2 | SB2/US5 | Patient | Analyze Chest X-Ray | I Can Identify Emphysema | 3 | DM
2 | SB2/US6 | Patient | Analyze Chest X-Ray | I Can Identify Fibrosis | 3 | CK
2 | SB2/US7 | Patient | Analyze Chest X-Ray | I Can Identify Effusion | 3 | PK
2 | SB2/US8 | Patient | Analyze Chest X-Ray | I Can Identify Viral Pneumonia | 3 | DM
2 | SB2/US9 | Patient | Analyze Chest X-Ray | I Can Identify Bacterial Pneumonia | 3 | CK
2 | SB2/US10 | Patient | Analyze Chest X-Ray | I Can Identify Cardiomegaly | 3 | PK
2 | SB2/US11 | Patient | Analyze Chest X-Ray | I Can Identify Nodule Mass | 3 | DM
2 | SB2/US12 | Patient | Analyze Chest X-Ray | I Can Identify Hernia | 3 | CK
2 | SB2/US13 | Patient | Analyze Chest X-Ray | I Can Identify Pleural_thickening | 3 | PK
2 | SB2/US14 | Administrator | Fire Select Queries | I Can View The Records | 5 | DM
2 | SB2/US15 | Administrator | Fire Update Queries | I Can Keep The Database Updated | 5 | CK
2 | SB2/US16 | Administrator | Fire Delete Queries | I Can Remove Unwanted Or Faulty Data | 5 | PK
2 | SB2/US17 | Administrator | Take Backup | I Can Save The Old Records In The Database For Future Use | 5 | DM
2 | SB2/US18 | Administrator | Delete Backup | I Can Delete The Records Which Is Not Needed Any More | 5 | CK
3 | SB3/US1 | Developer | Train Model For Covid19 Disease | Patient Can Analyze X-Ray Image For Covid19 | 2 | PK
3 | SB3/US2 | Developer | Train Model For Viral Pneumonia Disease | Patient Can Analyze X-Ray Image For Viral Pneumonia | 2 | DM
3 | SB3/US3 | Developer | Train Model For Bacterial Pneumonia Disease | Patient Can Analyze X-Ray Image For Bacterial Pneumonia | 2 | CK
3 | SB3/US4 | Developer | Train Model For Atelectasis Disease | Patient Can Analyze X-Ray Image For Atelectasis | 2 | PK
3 | SB3/US5 | Developer | Train Model For Consolidation Disease | Patient Can Analyze X-Ray Image For Consolidation | 2 | DM
3 | SB3/US6 | Developer | Train Model For Infiltration Disease | Patient Can Analyze X-Ray Image For Infiltration | 2 | CK
3 | SB3/US7 | Developer | Train Model For Pneumothorax Disease | Patient Can Analyze X-Ray Image For Pneumothorax | 2 | PK
3 | SB3/US8 | Developer | Train Model For Edema Disease | Patient Can Analyze X-Ray Image For Edema | 2 | DM
3 | SB3/US9 | Developer | Train Model For Emphysema Disease | Patient Can Analyze X-Ray Image For Emphysema | 2 | CK
3 | SB3/US10 | Developer | Train Model For Fibrosis Disease | Patient Can Analyze X-Ray Image For Fibrosis | 2 | PK
3 | SB3/US11 | Developer | Train Model For Effusion Disease | Patient Can Analyze X-Ray Image For Effusion | 2 | DM
3 | SB3/US12 | Developer | Train Model For Pleural_thickening Disease | Patient Can Analyze X-Ray Image For Pleural_thickening | 2 | CK
3 | SB3/US13 | Developer | Train Model For Cardiomegaly Disease | Patient Can Analyze X-Ray Image For Cardiomegaly | 2 | PK
3 | SB3/US14 | Developer | Train Model For Nodule Mass Disease | Patient Can Analyze X-Ray Image For Nodule Mass | 2 | DM
3 | SB3/US15 | Developer | Train Model For Hernia Disease | Patient Can Analyze X-Ray Image For Hernia | 2 | CK
3 | SB3/US16 | Developer | Train Model For Lung Opacity Problem | Patient Can Analyze X-Ray Image For Lung Opacity | 2 | PK
3 | SB3/US17 | Developer | Integrate All Models With Web System | Patient Can Easily Access It With Simple UI | 3 | DM
3 | SB3/US18 | Developer | Deploy My Models On Internet(Heroku/AWS) | Anyone Can Access It Over Internet | 4 | CK
4 | SB4/US1 | Developer | Use Terraform | I Can Configure My Web App Infrastructure | 4 | PK
4 | SB4/US2 | Developer | Launch One VPC in Mumbai with a public subnet | I Can Launch My Instances There | 4 | DM
4 | SB4/US3 | Developer | Configure AWS_internet_gateway | My Instance Can Have Internet Connectivity | 4 | CK
4 | SB4/US4 | Developer | Create an Ubuntu EC2 instance and log in to it | I Can Configure It For My Allpication | 4 | PK
4 | SB4/US5 | Developer | Install the requires libraries and packages | Dependency Error Will Not Occure | 4 | DM
4 | SB4/US6 | Developer | Configure Nginx And Gunicorn settings | I Can Launch My Web App | 4 | CK
4 | SB4/US7 | Developer | Have AI Chatbot Facility | My Users Can Have Medical Information About Chest Disease | 3 | DM
4 | SB4/US8 | Developer | Have Symptoms Assessment Facility In Bot | Users Can Use It For Disease Identification | 3 | CK
4 | SB4/US9 | Developer | Take Input Of Personal Detail Of Patient | I Can Keep Track Of Patients | 3 | PK
4 | SB4/US10 | Developer | Take Input Of Patient Symtoms | My Bot Can Analyze It | 3 | DM
4 | SB4/US11 | Developer | Provide Voice Based Input Facility | Patient Can Speak About Their Problem | 3 | CK
4 | SB4/US12 | Developer | Have Seprate Registration Form For ChatBot | Patient Can See Their Past Chats | 3 | PK
4 | SB4/US13 | Developer | Take Patient Feedback | Bot Can Understand The Patient Goals | 3 | DM
4 | SB4/US14 | Developer | Take Input In Text Form | My ChatBot Can Reply Accordingly | 3 | CK
4 | SB4/US15 | Developer | Provide First Aid Remedies | Immediate First Aid Facility Should Be Provided To Patient | 3 | PK
4 | SB4/US16 | Developer | Provide Healthy Health Tips | It Can Benefit The Patients | 3 | DM
4 | SB4/US17 | Developer | Integrate My Chatbot In Qurative Web System | It Will Be Available Their | 4 | CK

## Gantt Chart
GANTT CHART
PROJECT TITLE |  | Qurative.ai + AI Healthcare Chatbot |  |  |  | College NAME |  | Poornima Institute Of Engineering And Technology
PROJECT MANAGER |  | Mr. Deepak Moud |  |  |  | DATE |  | 2021-11-25
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | Phase 1 |  |  |  | Phase 2 |  |  | Phase 3 |  |  | Phase 4
[6 empty] | WEEK 1 | WEEK 2 |  | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12
1 | Project Backlog And Sprint Backlog Planning
1.1 | Product Backlog | DM+PK+CK | 2021-11-18 | 2021-11-21 | 3
1.2 | Sprint Backlog 1 & 2 | DM+PK+CK | 2021-11-22 | 2021-11-23 | 1
1.3 | Sprint Backlog 3 & 4 | DM+PK+CK | 2021-11-23 | 2021-11-24 | 1
2 | Performing Sprint Backlog 1 Task
2.1 | SB1 Initial 9 User Stories | DM+PK+CK | 2021-11-29 | 2021-12-05 | 7
2.2 | SB1 Final 10 User Stories | DM+PK+CK | 2021-12-06 | 2021-12-12 | 7
3 | Perform Sprint Backlog 2 Task
3.1 | SB2 Initial 9 User Stories | DM+PK+CK | 2021-12-13 | 2021-12-18 | 6
3.2 | SB2 Final 9 User Stories | DM+PK+CK | 2021-12-18 | 2021-12-24 | 7
4 | Perform Sprint Backlog 3
4.1 | SB3 Initial 9 User Stories | DM+PK+CK | 2022-02-01 | 2022-02-06 | 6
4.2 | SB3 Final 9 User Stories | DM+PK+CK | 2022-02-07 | 2022-02-12 | 6
5 | Perform Sprint Backlog 4 Task
5.1 | SB4 Initial 9 User Stories | DM+PK+CK | 2022-02-13 | 2022-02-19 | 7
5.2 | SB4 Final 8 User Stories | DM+PK+CK | 2022-02-19 | 2022-02-26 | 7

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Qurative AI System>
SB1/US1 | As A Patient I Want To Register Myself Using Phone Number So That I Can Receive A Confirmation/Verification Message | SB1/US1/T1 | Install OTP Login Plugins | CK+DM+PK | NOT STARTED
|  | SB1/US1/T2 | Using Google Firebase | CK+DM+PK | NOT STARTED
|  | SB1/US1/T3 | Integrating APIs To Our Project | CK+DM+PK | NOT STARTED
|  | SB1/US1/T4 | Creating A Project On Firebase And Use It For Authentication Purpose | CK+DM+PK | NOT STARTED
SB1/US2 | As A Patient I Want To Register Myself Using Personal Detail So That I Can Register My Self | SB1/US2/T1 | Create GUI Of Form Using HTML,CSS | CK+DM+PK | NOT STARTED
|  | SB1/US2/T2 | Provide Client Side Validation | CK+DM+PK | NOT STARTED
|  | SB1/US2/T3 | Sent A Confirmation Mail For Successful Registration Using Python | CK+DM+PK | NOT STARTED
SB1/US3 | As A Patient I Want To Receive A Confirmation Message/OTP So That I Can Access The Qurative.ai System | SB1/US3/T1 | Varification Of User Phone Number / Email | CK+DM+PK | NOT STARTED
|  | SB1/US3/T2 | Create Project On Firebase For Sending OTP | CK+DM+PK | NOT STARTED
|  | SB1/US3/T3 | Sending OTP Through Firebase | CK+DM+PK | NOT STARTED
SB1/US4 | As A Patient I Want To Login Into The System Using EMail Id And Password So That I Can Succesfully Login To The System | SB1/US4/T1 | Design A GUI For Login Form | CK+DM+PK | NOT STARTED
|  | SB1/US4/T2 | Perform Client Side Validation | CK+DM+PK | NOT STARTED
|  | SB1/US4/T3 | Checking User Entry In Sqlite Database | CK+DM+PK | NOT STARTED
|  | SB1/US4/T4 | On Successfull Login Navigate User To System | CK+DM+PK | NOT STARTED
SB1/US5 | As A Patient I Want To Write Comments So That I Can Share My Experience | SB1/US5/T1 | Design A GUI For Comment Section | CK+DM+PK | NOT STARTED
|  | SB1/US5/T2 | Show Previous Comments | CK+DM+PK | NOT STARTED
|  | SB1/US5/T3 | Post To Add New Comments / Feedback | CK+DM+PK | NOT STARTED
|  | SB1/US5/T4 | Testing Of The Module | CK+DM+PK | NOT STARTED
SB1/US6 | As A Patient I Want To Get Contact Support So That I Can Ask My Query | SB1/US6/T1 | Design A GUI For Contact Page | CK+DM+PK | NOT STARTED
|  | SB1/US6/T2 | User Will Ask Their Query | CK+DM+PK | NOT STARTED
|  | SB1/US6/T3 | Send Notification To Dev Team Using Python | CK+DM+PK | NOT STARTED
|  | SB1/US6/T4 | Testing Of The Module | CK+DM+PK | NOT STARTED
SB1/US7 | As A Patient I Want To Know About System Developer So That I Can Know Them | SB1/US7/T1 | Design A GUI For About Us Page | CK+DM+PK | NOT STARTED
|  | SB1/US7/T2 | Adding Information Regarding Devlopers | CK+DM+PK | NOT STARTED
|  | SB1/US7/T3 | Adding Social Media Handle Of Dev Team | CK+DM+PK | NOT STARTED
SB1/US8 | As A Patient I Want To Have A Responsive Web-System So That I Can Access It In Different Resolution Devices | SB1/US8/T1 | Learn CSS Frameworks (Bootstrap, Tailwind) For Responsive UI | CK+DM+PK | NOT STARTED
|  | SB1/US8/T2 | Learn Javascript | CK+DM+PK | NOT STARTED
|  | SB1/US8/T3 | Integrate Css With HTML Frontend | CK+DM+PK | NOT STARTED
|  | SB1/US8/T4 | Testing Of The Module | CK+DM+PK | NOT STARTED
SB1/US9 | As A Patient I Want To Know About Term And Condition Of Product So That I Am Aware Of System Usage Policy | SB1/US9/T1 | Design A GUI For T&C Page | CK+DM+PK | NOT STARTED
|  | SB1/US9/T2 | Make UI Responsive | CK+DM+PK | NOT STARTED
|  | SB1/US9/T3 | Regularly Updating The Policies | CK+DM+PK | NOT STARTED
|  | SB1/US9/T4 | Testing Of The Module | CK+DM+PK | NOT STARTED
SB1/US10 | As A Patient I Want To Have Optimized WebSystem So That It Works In Low Internet Connection Also | SB1/US10/T1 | Using Offline CSS Frameworks | CK+DM+PK | NOT STARTED
|  | SB1/US10/T2 | Minimal Use Of Large Files | CK+DM+PK | NOT STARTED
|  | SB1/US10/T3 | Testing Of System On Browser's Dev Mode Using Network Throttling | CK+DM+PK | NOT STARTED
|  | SB1/US10/T4 | Testing Of The Module | CK+DM+PK | NOT STARTED
SB1/US11 | As A Patient I Want To Have Description For All Chest Disease So That Patient Can I Can Understand Disease Well | SB1/US11/T1 | Studing Various Chest Diseases | CK+DM+PK | NOT STARTED
|  | SB1/US11/T2 | Creating GUI Chest Diseases Page | CK+DM+PK | NOT STARTED
|  | SB1/US11/T3 | Regularly Updating Chest Diseases Content | CK+DM+PK | NOT STARTED
|  | SB1/US11/T4 | Testing Of The Module | CK+DM+PK | NOT STARTED
SB1/US12 | As A Patient I Want To Have SSL Encrypted WebSystem So That Access Is Secure | SB1/US12/T1 | Learning AWS Certificate Manager | CK+DM+PK | NOT STARTED
|  | SB1/US12/T2 | Configuring ACM Service | CK+DM+PK | NOT STARTED
|  | SB1/US12/T3 | Get A Signed CA Certificate From AWS | CK+DM+PK | NOT STARTED
|  | SB1/US12/T4 | Testing Security Status For System | CK+DM+PK | NOT STARTED
SB1/US13 | As A Patient I Want To Upload My Chest X-Ray Image So That I Can Detect Dieseas If Exist | SB1/US13/T1 | Creating GUI For Upload The Image | CK+DM+PK | NOT STARTED
|  | SB1/US13/T2 | Process The Image Using Python Code | CK+DM+PK | NOT STARTED
|  | SB1/US13/T3 | Show The Result On GUI Using Jinja Module | CK+DM+PK | NOT STARTED
|  | SB1/US13/T4 | Testing Of The Module | CK+DM+PK | NOT STARTED
SB1/US14 | As A Patient I Want To Have Separate Prediction So That I Can Easily See Result Of All Dieseas | SB1/US14/T1 | Learn Javascript | CK+DM+PK | NOT STARTED
|  | SB1/US14/T2 | Design GUI With JS To Enable Separate Rendering | CK+DM+PK | NOT STARTED
|  | SB1/US14/T3 | Providing Seprate Result For Disease Tests | CK+DM+PK | NOT STARTED
|  | SB1/US14/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB1/US15 | As A Patient I Want To Analyze Chest X-Ray So That I Can Identify Covid19 | SB1/US15/T1 | Upload The Image Using GUI | CK+DM+PK | NOT STARTED
|  | SB1/US15/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB1/US15/T3 | Validate The Test Result | CK+DM+PK | NOT STARTED
|  | SB1/US15/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB1/US16 | As A Patient I Want To Know The Reason For Covid So That I Can Confirm The Covid | SB1/US16/T1 | Learn GRAD-CAM Algorithm | CK+DM+PK | NOT STARTED
|  | SB1/US16/T2 | Implement GRAD-CAM Using Python(Pytorch, Tensorflow) | CK+DM+PK | NOT STARTED
|  | SB1/US16/T3 | Integrate It With GUI | CK+DM+PK | NOT STARTED
|  | SB1/US16/T4 | Test The Module | CK+DM+PK | NOT STARTED
SB1/US17 | As A Patient I Want To Have Separate Report For Covid So That I Can Show It To Others | SB1/US17/T1 | Design GUI For Report | CK+DM+PK | NOT STARTED
|  | SB1/US17/T2 | Show Respective Report Result Using Jinja | CK+DM+PK | NOT STARTED
|  | SB1/US17/T3 | Show Output Of GRAD-CAM For Approval | CK+DM+PK | NOT STARTED
|  | SB1/US17/T4 | Test The Module | CK+DM+PK | NOT STARTED
SB1/US18 | As A Patient I Want To Download The Report Of Covid So That I Can Show It To Others | SB1/US18/T1 | Store The Result On Server | CK+DM+PK | NOT STARTED
|  | SB1/US18/T2 | Design GUI For Download Operation | CK+DM+PK | NOT STARTED
|  | SB1/US18/T3 | Use Python Code To Implement Download Operation | CK+DM+PK | NOT STARTED
|  | SB1/US18/T4 | Test The Module | CK+DM+PK | NOT STARTED
SB1/US19 | As A Patient I Want To Analyze Chest X-Ray So That I Can Identify Atelectasis | SB1/US19/T1 | Upload The Image Using GUI | CK+DM+PK | NOT STARTED
|  | SB1/US19/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB1/US19/T3 | Validate The Test Result | CK+DM+PK | NOT STARTED
|  | SB1/US19/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Completed Task
2021-11-29 | 150 |  | Tasks
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Qurative AI System>
SB2/US1 | As A Patient I Want to Analyze Chest X-Ray So that I Can Identify Consolidation | SB2/US1/T1 | Upload The Image For Checking Consolidation Problem In Chest | CK+DM+PK | NOT STARTED
|  | SB2/US1/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB2/US1/T3 | Validate And Show The Result On GUI | CK+DM+PK | NOT STARTED
|  | SB2/US1/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US2 | As A Patient I Want to Analyze Chest X-Ray So that I Can Identify Infilteration | SB2/US2/T1 | Upload The Image For Checking Infilteraton Problem In Chest | CK+DM+PK | NOT STARTED
|  | SB2/US2/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB2/US2/T3 | Validate And Show The Result On GUI | CK+DM+PK | NOT STARTED
|  | SB2/US2/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US3 | As A Patient I Want to Analyze Chest X-Ray So that I Can Identify Pneumothorax | SB2/US3/T1 | Upload The Image For Checking Pneumothorax Problem In Chest | CK+DM+PK | NOT STARTED
|  | SB2/US3/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB2/US3/T3 | Validate And Show The Result On GUI | CK+DM+PK | NOT STARTED
|  | SB2/US3/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US4 | As A Patient I Want to Analyze Chest X-Ray So that I Can Identify Edema | SB2/US4/T1 | Upload The Image For Checking Edema Problem In Chest | CK+DM+PK | NOT STARTED
|  | SB2/US4/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB2/US4/T3 | Validate And Show The Result On GUI | CK+DM+PK | NOT STARTED
|  | SB2/US4/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US5 | As A Patient I Want to Analyze Chest X-Ray So that I Can Identify Emphysema | SB2/US5/T1 | Upload The Image For Checking Emphysema Problem In Chest | CK+DM+PK | NOT STARTED
|  | SB2/US5/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB2/US5/T3 | Validate And Show The Result On GUI | CK+DM+PK | NOT STARTED
|  | SB2/US5/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US6 | As A Patient I Want to Analyze Chest X-Ray So that I Can Identify Fibrosis | SB2/US6/T1 | Upload The Image For Checking Fibrosis Problem In Chest | CK+DM+PK | NOT STARTED
|  | SB2/US6/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB2/US6/T3 | Validate And Show The Result On GUI | CK+DM+PK | NOT STARTED
|  | SB2/US6/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US7 | As A Patient I Want to Analyze Chest X-Ray So that I Can Identify Effusion | SB2/US7/T1 | Upload The Image For Checking Effusion Problem In Chest | CK+DM+PK | NOT STARTED
|  | SB2/US7/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB2/US7/T3 | Validate And Show The Result On GUI | CK+DM+PK | NOT STARTED
|  | SB2/US7/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US8 | As A Patient I Want to Analyze Chest X-Ray So that I Can Identify Viral Pneumonia | SB2/US8/T1 | Upload The Image For Checking Viral Pneumonia Problem In Chest | CK+DM+PK | NOT STARTED
|  | SB2/US8/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB2/US8/T3 | Validate And Show The Result On GUI | CK+DM+PK | NOT STARTED
|  | SB2/US8/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US9 | As A Patient I Want to Analyze Chest X-Ray So that I Can Identify Bacterial Pneumonia | SB2/US9/T1 | Upload The Image For Checking Bacterial Pneumonia Problem In Chest | CK+DM+PK | NOT STARTED
|  | SB2/US9/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB2/US9/T3 | Validate And Show The Result On GUI | CK+DM+PK | NOT STARTED
|  | SB2/US9/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US10 | As A Patient I Want to Analyze Chest X-Ray So that I Can Identify Cardiomegaly | SB2/US10/T1 | Upload The Image For Checking Cardiomegaly Problem In Chest | CK+DM+PK | NOT STARTED
|  | SB2/US10/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB2/US10/T3 | Validate And Show The Result On GUI | CK+DM+PK | NOT STARTED
|  | SB2/US10/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US11 | As A Patient I Want to Analyze Chest X-Ray So that I Can Identify Nodule Mass | SB2/US11/T1 | Upload The Image For Checking Nodule Mass Problem In Chest | CK+DM+PK | NOT STARTED
|  | SB2/US11/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB2/US11/T3 | Validate And Show The Result On GUI | CK+DM+PK | NOT STARTED
|  | SB2/US11/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US12 | As A Patient I Want to Analyze Chest X-Ray So that I Can Identify Hernia | SB2/US12/T1 | Upload The Image For Checking Hernia Problem In Chest | CK+DM+PK | NOT STARTED
|  | SB2/US12/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB2/US12/T3 | Validate And Show The Result On GUI | CK+DM+PK | NOT STARTED
|  | SB2/US12/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US13 | As A Patient I Want to Analyze Chest X-Ray So that I Can Identify Pleural_thickening | SB2/US13/T1 | Upload The Image For Checking Pleural_thickening Problem In Chest | CK+DM+PK | NOT STARTED
|  | SB2/US13/T2 | Click Submit To Process Image | CK+DM+PK | NOT STARTED
|  | SB2/US13/T3 | Validate And Show The Result On GUI | CK+DM+PK | NOT STARTED
|  | SB2/US13/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US14 | As A Administrator I Want to Fire Select Queries So that I Can View The Records | SB2/US14/T1 | Design The GUI | CK+DM+PK | NOT STARTED
|  | SB2/US14/T2 | Click To View Records | CK+DM+PK | NOT STARTED
|  | SB2/US14/T3 | Write SQL Select Query In Python execute() To View Records | CK+DM+PK | NOT STARTED
|  | SB2/US14/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US15 | As A Administrator I Want to Fire Update Queries So that I Can Keep The Database Updated | SB2/US15/T1 | Design The GUI | CK+DM+PK | NOT STARTED
|  | SB2/US15/T2 | Write SQL Select Query In Python execute() To Update Existing Records | CK+DM+PK | NOT STARTED
|  | SB2/US15/T3 | Close The SQL Connection On Complete | CK+DM+PK | NOT STARTED
|  | SB2/US15/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US16 | As A Administrator I Want to Fire Delete Queries So that I Can Remove Unwanted Or Faulty Data | SB2/US16/T1 | Design The GUI | CK+DM+PK | NOT STARTED
|  | SB2/US16/T2 | Click To Delete Records | CK+DM+PK | NOT STARTED
|  | SB2/US16/T3 | Delete The Wrong Entries And Faulty Data Using SQL In Python | CK+DM+PK | NOT STARTED
|  | SB2/US16/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US17 | As A Administrator I Want to Take Backup So that I Can Save The Old Records In The Database For Future Use | SB2/US17/T1 | Design The GUI | CK+DM+PK | NOT STARTED
|  | SB2/US17/T2 | Click To View Present Records | CK+DM+PK | NOT STARTED
|  | SB2/US17/T3 | Take Backup Of Old Data | CK+DM+PK | NOT STARTED
|  | SB2/US17/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED
SB2/US 18 | As A Administrator I Want to Delete Backup So that I Can Delete The Records Which Is Not Needed Any More | SB2/US18/T1 | Design The GUI | CK+DM+PK | NOT STARTED
|  | SB2/US18/T2 | Click To View Backup Records | CK+DM+PK | NOT STARTED
|  | SB2/US18/T3 | Delete Backup Records Using SQL delete Opeations | CK+DM+PK | NOT STARTED
|  | SB2/US18/T4 | Test The Complete Module | CK+DM+PK | NOT STARTED

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Completed Task
Tasks
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Qurative AI System>
SB3/US1 | As A Developer I Want To Train Model For Covid19 Disease So That Patient Can Analyze X-Ray Image For Covid19 | SB3/US1/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US1/T2 | Filtration Of Images Using Python From Available Dataset For Covid19 | CK+DM+PK | NOT STARTED
|  | SB3/US1/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US1/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Covid18 | CK+DM+PK | NOT STARTED
|  | SB3/US1/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US2 | As A Developer I Want To Train Model For Viral Pneumonia Disease So That Patient Can Analyze X-Ray Image For Viral Pneumonia | SB3/US2/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US2/T2 | Filtration Of Images Using Python From Available Dataset For Viral Pneumonia | CK+DM+PK | NOT STARTED
|  | SB3/US2/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US2/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Viral Pneumonia | CK+DM+PK | NOT STARTED
|  | SB3/US2/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US3 | As A Developer I Want To Train Model For Bacterial Pneumonia Disease So That Patient Can Analyze X-Ray Image For Bacterial Pneumonia | SB3/US3/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US3/T2 | Filtration Of Images Using Python From Available Dataset For Bacterial Pneumonia | CK+DM+PK | NOT STARTED
|  | SB3/US3/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US3/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Bacterial Pneumonia | CK+DM+PK | NOT STARTED
|  | SB3/US3/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US4 | As A Developer I Want To Train Model For Atelectasis Disease So That Patient Can Analyze X-Ray Image For Atelectasis | SB3/US4/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US4/T2 | Filtration Of Images Using Python From Available Dataset For Atelectasis | CK+DM+PK | NOT STARTED
|  | SB3/US4/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US4/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Atelectasis | CK+DM+PK | NOT STARTED
|  | SB3/US4/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US5 | As A Developer I Want To Train Model For Consolidation Disease So That Patient Can Analyze X-Ray Image For Consolidation | SB3/US5/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US5/T2 | Filtration Of Images Using Python From Available Dataset For Consolidation | CK+DM+PK | NOT STARTED
|  | SB3/US5/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US5/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Consolidation | CK+DM+PK | NOT STARTED
|  | SB3/US5/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US6 | As A Developer I Want To Train Model For Infiltration Disease So ThatPatient Can Analyze X-Ray Image For Infiltration | SB3/US6/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US6/T2 | Filtration Of Images Using Python From Available Dataset For Infiltration | CK+DM+PK | NOT STARTED
|  | SB3/US6/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US6/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Infiltration | CK+DM+PK | NOT STARTED
|  | SB3/US6/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US7 | As A Developer I Want To Train Model For Pneumothorax Disease So That Patient Can Analyze X-Ray Image For Pneumothorax | SB3/US7/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US7/T2 | Filtration Of Images Using Python From Available Dataset For Pneumothorax | CK+DM+PK | NOT STARTED
|  | SB3/US7/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US7/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Pneumothorax | CK+DM+PK | NOT STARTED
|  | SB3/US7/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US8 | As A Developer I Want To Train Model For Edema Disease So That Patient Can Analyze X-Ray Image For Edema | SB3/US8/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US8/T2 | Filtration Of Images Using Python From Available Dataset For Edema | CK+DM+PK | NOT STARTED
|  | SB3/US8/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US8/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Edema | CK+DM+PK | NOT STARTED
|  | SB3/US8/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US9 | As A Developer I Want To Train Model For Emphysema Disease So That Patient Can Analyze X-Ray Image For Emphysema | SB3/US9/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US9/T2 | Filtration Of Images Using Python From Available Dataset For Emphysema | CK+DM+PK | NOT STARTED
|  | SB3/US9/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US9/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Emphysema | CK+DM+PK | NOT STARTED
|  | SB3/US9/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US10 | As A Developer I Want To Train Model For Fibrosis Disease So That Patient Can Analyze X-Ray Image For Fibrosis | SB3/US10/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US10/T2 | Filtration Of Images Using Python From Available Dataset For Fibrosis | CK+DM+PK | NOT STARTED
|  | SB3/US10/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US10/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Fibrosis | CK+DM+PK | NOT STARTED
|  | SB3/US10/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US11 | As A Developer I Want To Train Model For Effusion Disease So That Patient Can Analyze X-Ray Image For Effusion | SB3/US11/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US11/T2 | Filtration Of Images Using Python From Available Dataset For Effusion | CK+DM+PK | NOT STARTED
|  | SB3/US11/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US11/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Effusion | CK+DM+PK | NOT STARTED
|  | SB3/US11/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US12 | As A Developer I Want To Train Model For Pleural_thickening Disease So That Patient Can Analyze X-Ray Image For Pleural_thickening | SB3/US12/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US12/T2 | Filtration Of Images Using Python From Available Dataset For Pleural_thickening | CK+DM+PK | NOT STARTED
|  | SB3/US12/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US12/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Pleural_thickening | CK+DM+PK | NOT STARTED
|  | SB3/US12/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US13 | As A Developer I Want To Train Model For Cardiomegaly Disease So That Patient Can Analyze X-Ray Image For Cardiomegaly | SB3/US13/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US13/T2 | Filtration Of Images Using Python From Available Dataset For Cardiomegaly | CK+DM+PK | NOT STARTED
|  | SB3/US13/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US13/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Cardiomegaly | CK+DM+PK | NOT STARTED
|  | SB3/US13/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US14 | As A Developer I Want To Train Model For Nodule Mass Disease So That Patient Can Analyze X-Ray Image For Nodule Mass | SB3/US14/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US14/T2 | Filtration Of Images Using Python From Available Dataset For Nodule Mass | CK+DM+PK | NOT STARTED
|  | SB3/US14/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US14/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Nodule Mass | CK+DM+PK | NOT STARTED
|  | SB3/US14/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US15 | As A Developer I Want To Train Model For Hernia Disease So That Patient Can Analyze X-Ray Image For Hernia | SB3/US15/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US15/T2 | Filtration Of Images Using Python From Available Dataset For Hernia | CK+DM+PK | NOT STARTED
|  | SB3/US15/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US15/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Hernia | CK+DM+PK | NOT STARTED
|  | SB3/US15/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US16 | As A Developer I Want To Train Model For Lung Opacity Problem So That Patient Can Analyze X-Ray Image For Lung Opacity | SB3/US16/T1 | Download Dataset From Kaggle | CK+DM+PK | NOT STARTED
|  | SB3/US16/T2 | Filtration Of Images Using Python From Available Dataset For Lung Opacity | CK+DM+PK | NOT STARTED
|  | SB3/US16/T3 | Perform Data Preprocessing On Collected Images | CK+DM+PK | NOT STARTED
|  | SB3/US16/T4 | Create A Binary Classifier Using Deep Learning CNN To Predict Normal Or Lung Opacity | CK+DM+PK | NOT STARTED
|  | SB3/US16/T5 | Check Model Accuracy And Test With Sample Image | CK+DM+PK | NOT STARTED
SB3/US17 | As A Developer I Want To Integrate All Models With Web System So That Patient Can Easily Access It With Simple UI | SB3/US17/T1 | Learn Python Flask For Backend | CK+DM+PK | NOT STARTED
|  | SB3/US17/T2 | Create And Manage All Routes And Write Respective Code | CK+DM+PK | NOT STARTED
|  | SB3/US17/T3 | Learn Jinja Templating And Integrate It With Python | CK+DM+PK | NOT STARTED
|  | SB3/US17/T4 | Test The Integration Whether All Models Are Working Fine Or Not | CK+DM+PK | NOT STARTED
SB3/US18 | As A Developer I Want To Deploy My Models On Internet(Heroku/AWS) So That Anyone Can Access It Over Internet | SB3/US18/T1 | Create Account On Aws/Heroku | CK+DM+PK | NOT STARTED
|  | SB3/US18/T2 | Configure The Platform For Python Application | CK+DM+PK | NOT STARTED
|  | SB3/US18/T3 | Deploy The Product | CK+DM+PK | NOT STARTED
|  | SB3/US18/T4 | Test Application At The Deployed URL | CK+DM+PK | NOT STARTED

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Completed Task
Tasks
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Qurative AI System>
SB4/US1 | As A Developer I Want To Use Terraform So That I Can Configure My Web App Infrastructure | SB4/US1/T1 | Learn Terraform IAAC(Infrastructure As A Code) | CK+DM+PK | NOT STARTED
|  | SB4/US1/T2 | Learn AWS Cloud Services | CK+DM+PK | NOT STARTED
|  | SB4/US1/T3 | Learning HCL Language For Terraform | CK+DM+PK | NOT STARTED
|  | SB4/US1/T4 | Create Account On AWS For Free Tier | CK+DM+PK | NOT STARTED
SB4/US2 | As A Developer I Want To Launch One VPC So That I Can Launch My Instances There | SB4/US2/T1 | Create A Security Group For VPC With Inbound And Outbound Traffic Policy | CK+DM+PK | NOT STARTED
|  | SB4/US2/T2 | Make A Public Subnet Using Terraform | CK+DM+PK | NOT STARTED
|  | SB4/US2/T3 | Create And Attach One Internet Gateway Using Terraform | CK+DM+PK | NOT STARTED
|  | SB4/US2/T4 | Create And Update Route Policy In Routing Table | CK+DM+PK | NOT STARTED
SB4/US3 | As A Developer I Want To Configure internet gateway So That My Instance Can Have Internet Connectivity | SB4/US3/T1 | Using aws_internet_gateway Resource From Terraform | CK+DM+PK | NOT STARTED
|  | SB4/US3/T2 | Provide vpc_id With Terraform Code | CK+DM+PK | NOT STARTED
|  | SB4/US3/T3 | Activate The Terraform Plugin For AWS And Build, Connect | CK+DM+PK | NOT STARTED
SB4/US4 | As A Developer I Want To Launch AMI EC2 instance So That I Can Configure My Web App Infrastructure | SB4/US4/T1 | Create A Key-Pair For Instance Security | CK+DM+PK | NOT STARTED
|  | SB4/US4/T2 | Provide AWS Ami, instance_id, Subnet_id And Other Information In Terraform | CK+DM+PK | NOT STARTED
|  | SB4/US4/T3 | Provide Instance Specification Information In HCL | CK+DM+PK | NOT STARTED
|  | SB4/US4/T4 | Create And Attach A Security Group With Traffic Rules | CK+DM+PK | NOT STARTED
SB4/US5 | As A Developer I Want To Install the requires libraries and packages So That Dependency Error Will Not Occure | SB4/US5/T1 | Create NULL Resource In Terraform | CK+DM+PK | NOT STARTED
|  | SB4/US5/T2 | Provide Host, Private Key And User Information In HCL | CK+DM+PK | NOT STARTED
|  | SB4/US5/T3 | Fetch Full App Code From Github On EC2 | CK+DM+PK | NOT STARTED
|  | SB4/US5/T4 | Provision The Instance With Required Packages(Python, Nginx, Gunicorn) | CK+DM+PK | NOT STARTED
SB4/US6 | As A Developer I Want To Configure Nginx And Gunicorn settings So That I Can Launch My Web App | SB4/US6/T1 | Install Nginx In EC2 | CK+DM+PK | NOT STARTED
|  | SB4/US6/T2 | Create a Config File With Proxy Pass Information | CK+DM+PK | NOT STARTED
|  | SB4/US6/T3 | Restart Nginx Services | CK+DM+PK | NOT STARTED
|  | SB4/US6/T4 | Configuring Gunicorn service With Respective Services And Test Application | CK+DM+PK | NOT STARTED
SB4/US7 | As A Developer I Want To Have AI Chatbot Facility So That My Users Can Have Medical Information About Chest Disease | SB4/US7/T1 | Learn About Chatterbot And Chatterbot Corpus In Python | CK+DM+PK | NOT STARTED
|  | SB4/US7/T2 | Design GUI For AI ChatBot On System | CK+DM+PK | NOT STARTED
|  | SB4/US7/T3 | Create An Sqlite Database To Store The Conversion Dataset | CK+DM+PK | NOT STARTED
|  | SB4/US7/T4 | Integrate Chatbot With The Web System | CK+DM+PK | NOT STARTED
SB4/US8 | As A Developer I Want To Have Symptoms Assessment Facility In Bot So That Users Can Use It For Disease Identification | SB4/US8/T1 | Build GUI For Updating Training Dataset | CK+DM+PK | NOT STARTED
|  | SB4/US8/T2 | Train The Model With Available Conversations | CK+DM+PK | NOT STARTED
|  | SB4/US8/T3 | Update Database With The Symptoms Conversations And Again Train | CK+DM+PK | NOT STARTED
|  | SB4/US8/T4 | Test The Module | CK+DM+PK | NOT STARTED
SB4/US9 | As A Developer I Want To Take Input Of Personal Detail Of Patient So That I Can Keep Track Of Patients | SB4/US9/T1 | Build GUI For Taking Input Of Patients Details | CK+DM+PK | NOT STARTED
|  | SB4/US9/T2 | Provide Input Validation For Details At Client Level | CK+DM+PK | NOT STARTED
|  | SB4/US9/T3 | Store The Information In Sqlite Database | CK+DM+PK | NOT STARTED
|  | SB4/US9/T4 | Test The Module Build | CK+DM+PK | NOT STARTED
SB4/US10 | As A Developer I Want To Take Input Of Patient Symtoms So That My Bot Can Analyze It | SB4/US10/T1 | Build GUI For Taking Input From Patient | CK+DM+PK | NOT STARTED
|  | SB4/US10/T2 | Process The Input With AI ChatBot Using Python | CK+DM+PK | NOT STARTED
|  | SB4/US10/T3 | Provide The Corrosponding Response On GUI | CK+DM+PK | NOT STARTED
|  | SB4/US10/T4 | Test The Corrosponding Module | CK+DM+PK | NOT STARTED
SB4/US11 | As A Developer I Want To Provide Voice Based Input Facility So That Patient Can Speak About Their Problem | SB4/US11/T1 | Learn Pyttsx3 And SpeechRecognition | CK+DM+PK | NOT STARTED
|  | SB4/US11/T2 | Import The Modules And Write Corrosponding Code | CK+DM+PK | NOT STARTED
|  | SB4/US11/T3 | Convert The Speech Into Text | CK+DM+PK | NOT STARTED
|  | SB4/US11/T4 | Test The Module | CK+DM+PK | NOT STARTED
SB4/US12 | As A Developer I Want To Have Seprate Registration Form For ChatBot So That Patient Can See Their Past Chats | SB4/US12/T1 | Build GUI For Seprate Registration Form | CK+DM+PK | NOT STARTED
|  | SB4/US12/T2 | Write Select Query In Python So That User Can Filter Data Based On His Identity | CK+DM+PK | NOT STARTED
|  | SB4/US12/T3 | Show The Result On GUI Using Jinja Templating | CK+DM+PK | NOT STARTED
|  | SB4/US12/T4 | Test The Module | CK+DM+PK | NOT STARTED
SB4/US13 | As A Developer I Want To Take Patient Feedback So That Bot Can Understand The Patient Goals | SB4/US13/T1 | Build GUI For Taking The Feedback | CK+DM+PK | NOT STARTED
|  | SB4/US13/T2 | Store The Feedback Into Sqlite Database | CK+DM+PK | NOT STARTED
|  | SB4/US13/T3 | Write Select Query In Python To Update Database Of Conversations | CK+DM+PK | NOT STARTED
|  | SB4/US13/T4 | Train The Bot On The Basis Of New Conversations And Test | CK+DM+PK | NOT STARTED
SB4/US14 | As A Developer I Want To Take Input In Text Form So That My ChatBot Can Reply Accordingly | SB4/US14/T1 | Provide Facility To Take Input From GUI | CK+DM+PK | NOT STARTED
|  | SB4/US14/T2 | Process The Text To Get Result From Chatbot | CK+DM+PK | NOT STARTED
|  | SB4/US14/T3 | Show Result On UI | CK+DM+PK | NOT STARTED
|  | SB4/US14/T4 | Test The Working Of This Module | CK+DM+PK | NOT STARTED
SB4/US15 | As A Developer I Want To Provide First Aid Remedies So That Immediate First Aid Facility Should Be Provided To Patient | SB4/US15/T1 | Update The Conversation Database With The First Aid Remedies | CK+DM+PK | NOT STARTED
|  | SB4/US15/T2 | Again Retrain The Model With The Updated Data Entries | CK+DM+PK | NOT STARTED
|  | SB4/US15/T3 | Show The Result On GUI Using Jinja | CK+DM+PK | NOT STARTED
|  | SB4/US15/T4 | Test The Retrained Model | CK+DM+PK | NOT STARTED
SB4/US16 | As A Developer I Want To Provide Healthy Health Tips So That It Can Benefit The Patients | SB4/US16/T1 | Update The Conversation Database With The Healthy Health Tips | CK+DM+PK | NOT STARTED
|  | SB4/US16/T2 | Again Retrain The Model With The Updated Data Entries | CK+DM+PK | NOT STARTED
|  | SB4/US16/T3 | Show The Result On GUI Using Jinja | CK+DM+PK | NOT STARTED
|  | SB4/US16/T4 | Test The Retrained Model | CK+DM+PK | NOT STARTED
SB4/US17 | As A Developer I Want To Integrate My Chatbot In Qurative Web System So That It Will Be Available Their | SB4/US17/T1 | Use Flask And Integrate The Chatbot To The Web System | CK+DM+PK | NOT STARTED
|  | SB4/US17/T2 | Use Jinja And Flask Routing To Render Suitable Template | CK+DM+PK | NOT STARTED
|  | SB4/US17/T3 | Check Connectivity Of Application With Localhost | CK+DM+PK | NOT STARTED
|  | SB4/US17/T4 | Test The Module Whether Integration Is Succesfull Or Not | CK+DM+PK | NOT STARTED

## SB BD Ch04
Date | Planned Total Task | Actual Completed Task
Tasks
Days